## Sheet1
Screen | Task | Sub Task | Start_Date | End_Date | Original_End_Date | Reason/Comment | Assigned_to | Report_to
Home Screen | update or delete posts | 1. Create function in Social_DB to update post table in mysql and mongoDB | 2022-04-10 | 2022-04-11 |  |  | Rohit | Sonali
Social |  | 2. Create a function in social_article in core to folder | 2022-04-10 | 2022-04-11 |  |  | Rohit | Sonali
|  | 3. Create an endpoint in Social_ns for this | 2022-04-10 | 2022-04-11 |  |  | Rohit | Sonali
[7 empty] | Rohit | Sonali
| create or update social groups | 1. Create an endpoint for group creation | 2022-04-10 | 2022-04-12 |  |  | Rohit | Sonali
|  | 2. Create functions for saving group details and editing them | 2022-04-10 | 2022-04-12 |  |  | Rohit | Sonali
took leave | took leave | took leave | 2022-04-25 | 2022-04-29 |  | due to mid sem examination | Rohit | Sonali
Profile Screen | Create functions to upload data in profile(company/ngo) with a file | 1. create an endpoint to upload xls/xlsx/csv file | 2022-04-30 | 2022-05-01 | 2022-05-01 | subtask is completed before deadline | Rohit | Sonali
Upload |  | 2. create a function to read data from documets and upload to a folder and store relevant data in a table or in mongoDB | 2022-05-02 | 2022-05-03 | 2022-05-05 | task was completed on time but had to do some changes after meeting | Rohit | Sonali
Appointment | create appointment sechduler | 1. create appointment booking endpoint | 2022-05-06 | 2022-05-07 | 2022-05-07 | subtask is completd on time
|  | 2. create appointment cancellation endpoint | 2022-05-08 | 2022-05-09 | 2022-05-09 | subtask is completd on time
|  | 3. create appointment updation endpoint | 2022-05-10 | 2022-05-11 | 2022-05-11 | subtask is completd on time
|  | 4. create appointment checking endpoint | 2022-05-12 | 2022-05-13 | 2022-05-13 | subtask is completd on time
subtask was completed on time for user side but didnt had idea that i have to add doctor dashnoard also
Doctor | create doctor dashboard | 1. Create an endpoint for information update | 2022-05-14 | 2022-05-17 | 2022-05-15 | i comleted the subtask on time without doctor id because i didn't had it,after reciving doctor id from mam i had to modified the code
|  | 2.create an endpoint for updating working status | 2022-05-18 | 2022-05-19 | 2022-05-19 | subtask is completd on time
Appointment ,Doctor | Create sms alert via mobile number and email | 1.Add message alert via mobile number | 2022-05-20 | 2022-05-20 | 2022-05-20 | subtask is postponed due to not getting proper api
|  | 2.Add message alert via email | 2022-05-21 | 2022-05-21 | 2022-05-21 | subtask is complete on time
|  | 3.Add message alert via whastapp | 2022-05-22 | 2022-05-22 | 2022-05-23 | subtask is completed before time
4 leave remaining from 25-04-2022 to 23-05-2022